## Sprint Plan
AI-enabled Smart Market Linkage Platform (SHG) - POC Development Sprint Plan
Scope: development only - architecture diagrams, technical documents & code. ¦ 6 one-week sprints (Sprint 0-5), parallel workstreams. ¦ Tasks consolidated by module; each row lists the exact steps to perform.
Task ID | Sprint | Module | Component / Task | What To Do (exact steps) | Complexity | Est. (pd) | Tech / Tools | Depends On | Deliverable | Status
T01 | Sprint 0 | Foundation & Architecture | Architecture diagrams & tech design | 1. Draw C4 System-Context diagram: SHG users, ULB/district/state officials, admin, and external systems (MEPMA, ONDC, GeM, Agmarknet, WhatsApp, Bhashini). 2. Draw Container diagram: React PWA, Core API (NestJS), ML services (FastAPI), Notification service, PostgreSQL/PostGIS/pgvector, Redis, object storage. 3. Draw the voice data-flow diagram (mic -> ASR -> NLU -> dialogue -> action -> TTS) and the recommendation data-flow diagram. 4. Draw the deployment diagram (India-region cloud, containers, network, secrets, CDN). 5. Write short ADRs (Architecture Decision Records) for each major stack choice with rationale. 6. Export all diagrams as PNG/SVG and commit them plus the design doc to /docs in the repo. | High | 3 | draw.io / C4 model, Markdown (ADRs) | - | Architecture doc + diagram set in /docs | Not Started
T02 | Sprint 0 | Foundation & Architecture | Database schema & migrations | 1. Model core entities: users, roles, shg, product, product_image, buyer, sales, enquiry, recommendation, notification, consent, audit_log. 2. Model master data: category, district, ulb, mandal, festival_calendar. 3. Add PostGIS geometry columns for shg/product/buyer location; add pgvector columns for product/buyer embeddings. 4. Define foreign keys, indexes and constraints; draw the ER diagram. 5. Implement migrations (Prisma or TypeORM) and seed scripts for master data. 6. Run migrations on a fresh DB and confirm they apply cleanly; commit ER diagram to /docs. | High | 3 | PostgreSQL 16, PostGIS, pgvector, Prisma/TypeORM, dbdiagram | T01 | Migrations + ER diagram | Not Started
T03 | Sprint 0 | Foundation & Architecture | Repo scaffold, CI/CD & environments | 1. Create a mono-repo (Nx/Turborepo) with apps: web, core-api, ml-services, notification-service, plus shared libs. 2. Configure ESLint, Prettier, Husky pre-commit hooks and a shared tsconfig. 3. Write Dockerfiles per service and a docker-compose for local dev (Postgres+PostGIS, Redis, MinIO). 4. Set up GitHub Actions: lint -> test -> build -> push image, on push/PR. 5. Provision dev + staging on an India-region cloud (or write Terraform for it) with a secrets manager and env config. 6. Verify the full stack boots locally and CI is green on the scaffold commit. | Medium | 2 | Nx/Turborepo, Docker, docker-compose, GitHub Actions, Terraform | T01 | Green CI + runnable local stack | Not Started
T04 | Sprint 0 | Foundation & Architecture | Design system & UI wireframes | 1. Define design tokens (colours, spacing, typography incl. Noto Sans Telugu) and build a Tailwind base theme. 2. Build a reusable component library: buttons, inputs, cards, tables, modals, chart wrappers. 3. Set up i18n (react-i18next) with Telugu/English resource files and a language toggle. 4. Create wireframes for registration, product catalogue, voice assistant, all dashboards and admin. 5. Build the responsive mobile-first app shell + PWA manifest and service-worker base. | Medium | 3 | Figma, React, TypeScript, Tailwind, react-i18next, PWA | T01 | Component library + wireframes | Not Started
T05 | Sprint 0 | Foundation & Architecture | Core API framework + Auth/RBAC | 1. Bootstrap the NestJS core-api: config module, structured logging, global exception filter, /health, Swagger. 2. Build phone-OTP login: request-OTP endpoint (sends SMS), verify-OTP -> issue JWT access + refresh tokens. 3. Implement RBAC roles (SHG, ULB official, district official, state official, admin) with a role guard + permission decorators. 4. Add scoping middleware so officials only see their district/ULB data. 5. Build user CRUD + role-assignment endpoints; write unit tests for the auth flows. | Medium | 3 | NestJS, JWT, Redis, Swagger, Jest | T02,T03 | Auth + protected routes + Swagger | Not Started
T06 | Sprint 1 | Module 1 - SHG Product Registry | Registry backend (SHG + product + image + geo) | 1. Build SHG entity + CRUD (/shgs): profile, type, production capacity, bank details, geo. 2. Build Product entity + CRUD (/products) linked to SHG: name, category, description, unit, price, MOQ, stock, availability. 3. Build image upload endpoint: accept multipart, validate, resize + thumbnail with Sharp, virus-scan, store to S3/MinIO, save URLs. 4. Build geo-tagging: accept lat/long, reverse-geocode to district/ULB/mandal, store as a PostGIS point; add a 'products near me' geo-query. 5. Add validation (class-validator), pagination and filtering by category/district; seed demo data; expose everything via Swagger. | High | 4 | NestJS, PostgreSQL, PostGIS, Sharp, S3/MinIO, ClamAV | T05 | SHG + product + image + geo APIs | Not Started
T07 | Sprint 1 | Module 1 - SHG Product Registry | Registry frontend (register + catalogue + camera) | 1. Build the mobile-first SHG registration flow: multi-step, large touch targets, Telugu labels, minimal typing. 2. Build product catalogue screens: list, add/edit product with price & capacity, and a category picker. 3. Build in-browser camera capture + gallery upload with upload progress and retry for weak networks. 4. Wire all screens to the registry APIs; add an offline queue (IndexedDB) that syncs when back online. 5. Add form validation and the Telugu/English toggle across all screens. | High | 4 | React, TypeScript, Tailwind, MediaDevices API, PWA, IndexedDB | T06,T04 | Registry web/PWA UI | Not Started
T08 | Sprint 1 | Module 1 - SHG Product Registry | Product categorization AI | 1. Create a FastAPI ML endpoint POST /categorize. 2. Build a text classifier: fine-tune/prompt IndicBERT on product name + description to predict the taxonomy category. 3. (Optional) Add an image classifier (CLIP/ViT) to assist categorization from the product photo. 4. Return the top-3 category suggestions with confidence scores. 5. Integrate into the product-create flow as a suggestion with a human override. | High | 3 | Python, FastAPI, IndicBERT, CLIP/ViT, scikit-learn | T06 | Categorization API integrated | Not Started
T09 | Sprint 1 | Admin Portal | Admin backend + frontend | 1. Build admin backend endpoints: manage users/SHGs/products, manage master data (categories, districts, ULBs, mandals, festival calendar), approve/flag content. 2. Build the admin frontend: auth-gated layout, role-based menu, data tables with search/filter/pagination. 3. Build CRUD forms for all master data. 4. Add summary tiles (counts of SHGs / products / users) on the admin home. | Medium | 3 | NestJS, React, TypeScript | T05,T06 | Admin portal (backend + UI) | Not Started
T10 | Sprint 2 | Module 2 - Voice AI Assistant | Voice pipeline backend (ASR / TTS / dialogue) | 1. Build a FastAPI voice-service with a WebSocket streaming endpoint for audio. 2. Integrate ASR (Bhashini / AI4Bharat IndicASR) for Telugu + English speech-to-text; handle chunked audio and background noise. 3. Integrate TTS (Bhashini / Indic-TTS) for text-to-speech with response caching. 4. Store conversation session/state in Redis and manage multi-turn context. 5. Build an action dispatcher that calls core-api for product registration, market/price enquiry and buyer search. | High | 4 | Python, FastAPI, WebSocket, Bhashini/AI4Bharat, Redis | T05 | Voice pipeline service | Not Started
T11 | Sprint 2 | Module 2 - Voice AI / Telugu NLP | Telugu NLP + intent & dialogue models | 1. Build an intent classifier for: product registration, market enquiry, price enquiry, buyer search, scheme guidance (fine-tune IndicBERT). 2. Build an entity extractor for product, quantity, place and price (IndicNLP / spaCy). 3. Implement transliteration and text normalization (Roman <-> Telugu). 4. Build a slot-filling dialogue manager with clarification and fallback handling. 5. Evaluate WER and intent F1 on a Telugu test set and tune until recognition reaches the >=90% target. | High | 4 | IndicBERT, AI4Bharat IndicNLP, spaCy, indic-trans, jiwer | T10 | NLU/dialogue models + eval report | Not Started
T12 | Sprint 2 | Module 2 - Voice AI Assistant | Scheme guidance (RAG) + assistant frontend | 1. Collect and structure Government scheme documents for SHGs; chunk and embed them into pgvector. 2. Build a retrieval + LLM answer endpoint grounded on the retrieved chunks (with source citations); wire the scheme-guidance intent to it. 3. Build the assistant UI: push-to-talk mic capture, live waveform and streaming transcript. 4. Add a text-input fallback + chat transcript, play TTS replies, and show action results (e.g. 'product registered'). 5. Add low-bandwidth mode and the Telugu/English toggle. | High | 4 | pgvector, embeddings, LLM/RAG, React, WebAudio, WebSocket | T11 | Scheme Q&A + assistant UI | Not Started
T13 | Sprint 2 | Module 6 - Notification Engine | Notification core + all channels | 1. Build the notification-service: template engine, provider abstraction, BullMQ queue, retries and delivery logs. 2. Integrate SMS (MSG91/Gupshup with DLT templates) - this also powers OTP. 3. Integrate WhatsApp Business API to send templated messages and receive replies. 4. Integrate voice alerts (Exotel IVR + TTS) and email (Amazon SES). 5. Wire domain events (buyer enquiry, demand increase, price change, tender opportunity) to fire the right notifications. | High | 4 | NestJS, BullMQ/Redis, MSG91, WhatsApp Business API, Exotel, SES | T05 | Multi-channel notification engine | Not Started
T14 | Sprint 3 | Module 3 - AI Market Intelligence | Data & feature pipeline | 1. Build ingestion for sales, enquiries, prices (Agmarknet) and product data. 2. Clean the data and engineer features: seasonality, festival calendar, geo (district / H3 cell) and lag features. 3. Store features as Parquet / feature tables and schedule a periodic refresh. | High | 3 | Python, Pandas, Parquet, cron/Airflow-lite | T02 | Reproducible feature pipeline | Not Started
T15 | Sprint 3 | Module 3 - AI Market Intelligence | Forecasting models + MI APIs | 1. Build a demand-forecasting model (Prophet/XGBoost) per product x district with seasonality + festival regressors. 2. Build a price trend + short-horizon price-forecast model. 3. Backtest both, compute error metrics and register the models. 4. Geo-cluster demand into hotspots (H3 + clustering) and compute best-selling locations. 5. Serve everything via FastAPI: /forecast/demand, /forecast/price, /hotspots, /seasonality. | High | 4 | Prophet, XGBoost, Darts, scikit-learn, H3, FastAPI | T14 | Market-intelligence APIs | Not Started
T16 | Sprint 3 | Module 4 - Buyer Matching Engine | Buyer registry backend | 1. Model buyers (institutional / retail / bulk / government-procurement) with demand profiles, categories and locations. 2. Build buyer CRUD + import endpoints. 3. Seed sample buyers and GeM procurement opportunities. | Medium | 2 | NestJS, PostgreSQL | T02 | Buyer registry APIs | Not Started
T17 | Sprint 3 | Module 4 - Buyer Matching Engine | Recommender + ranking + score + explainability | 1. Compute product and buyer embeddings and store them in pgvector / FAISS. 2. Build a hybrid recommender (content similarity + collaborative signals). 3. Compute a match score and expected demand for each SHG-buyer pair. 4. Add a learning-to-rank layer (LightGBM) to order the recommendations. 5. Generate human-readable explanations (SHAP + templates) for why each buyer is recommended. 6. Serve GET /recommendations/{shgId} and capture accept/reject feedback for retraining. | Very High | 5 | embeddings, FAISS/pgvector, LightFM, LightGBM, SHAP, FastAPI | T14,T16 | Recommendation API with reasons | Not Started
T18 | Sprint 4 | Analytics (shared) | Analytics aggregation backend | 1. Build materialized views / metrics for SHGs, products, sales, enquiries, recommendations and buyers. 2. Build filterable, drill-down aggregation APIs (by district/ULB/category/date) with caching and pagination. | High | 3 | PostgreSQL materialized views, NestJS, Redis | T06,T17 | Metrics / aggregation APIs | Not Started
T19 | Sprint 4 | Module 5 - Market Linkage Dashboard | Dashboards + heat maps (frontend) | 1. Build the District, ULB, SHG, Product and Buyer dashboards with drill-down. 2. Build sales-analytics and recommendation-analytics views (coverage, acceptance, success). 3. Build interactive demand/activity heat maps (Leaflet/Mapbox + H3). 4. Add filters (district/ULB/category/date) and export to PDF/Excel. | High | 4 | React, ECharts/Recharts, Leaflet/Mapbox GL | T18 | Market-linkage dashboards | Not Started
T20 | Sprint 4 | Module 7 - Government Dashboard | Govt dashboard (frontend) | 1. Build KPI tiles: registered SHGs, products, uptime, satisfaction, enquiries generated. 2. Build the state demand heatmap plus buyer-activity and market-linkage panels. 3. Build district-ranking, product-performance and recommendation-success panels. | Medium | 3 | React, ECharts, Leaflet/Mapbox | T18 | Government dashboard | Not Started
T21 | Sprint 4 | External Integrations | MEPMA + Agmarknet + ONDC + GeM | 1. MEPMA SHG DB: build an API/ETL sync with identity mapping + dedupe (simulate with realistic data if no live API). 2. Agmarknet: build scheduled price ingestion (data.gov.in) feeding the feature pipeline and dashboards. 3. ONDC: build a seller-side catalogue-publishing adapter (Beckn protocol, request signing/keys) or demonstrate readiness. 4. GeM: map procurement opportunities to products (API/feed or simulated) and trigger tender alerts. 5. Write integration tests with simulated fallbacks for every external system. | Very High | 5 | REST/ETL, ONDC/Beckn, data.gov.in API, Postman/Newman | T06,T13,T16 | Working / simulated integrations | Not Started
T22 | Sprint 5 | Security & DPDP Compliance | Consent, encryption, audit, hardening | 1. Build consent management: consent capture, purpose logging, withdrawal and privacy notices (per DPDP Act 2023). 2. Enforce encryption at rest (pgcrypto/KMS) and TLS in transit; encrypt PII fields. 3. Add tamper-evident audit logging and access logs across services. 4. Implement the right-to-erasure / data-access request workflow. 5. Security hardening: OWASP Top-10 pass, rate limiting, input validation, dependency scan (Snyk) and a secrets audit. | High | 4 | NestJS, pgcrypto, KMS, OWASP ZAP, Snyk | T05 | DPDP-compliant, hardened build | Not Started
T23 | Sprint 5 | Testing & Stabilization | Performance, E2E & fixes | 1. Load-test to validate the <3s average response and >=99% uptime targets (k6/Locust). 2. Run automated end-to-end tests across all modules (Playwright). 3. Re-validate >=90% Telugu voice accuracy on a holdout set. 4. Triage and fix defects to release quality (zero open P0/P1). | High | 3 | k6/Locust, Playwright, jiwer | T19,T20,T21 | Test reports + stabilized build | Not Started
T24 | Sprint 5 | Documentation & Deployment | Docs, API reference & deploy | 1. Write the technical documentation: architecture, data model, ML model cards and runbooks. 2. Publish API documentation (OpenAPI/Swagger) for every service. 3. Write the deployment guide (step-by-step). 4. Deploy to a production-like India-region environment (blue/green + rollback) and set up monitoring, alerting and backups. | Medium | 3 | Markdown, Swagger, Docker/K8s, Terraform, Prometheus/Grafana | T22,T23 | Docs + live POC deployment | Not Started
TOTAL | 24 development tasks |  |  |  |  | 83

## Sprint Summary
Sprint Summary - development track
Sprint | Week | Focus (modules built) | Tasks | What's working by end of sprint
Sprint 0 | W1 | Foundation & Architecture | T01-T05 | Diagrams, DB schema, repo/CI-CD, design system, core API with OTP auth + RBAC.
Sprint 1 | W2 | Module 1 Registry + Admin | T06-T09 | SHGs & products register end-to-end (web/PWA); auto-categorization; admin manages master data.
Sprint 2 | W3 | Module 2 Voice + Module 6 Notify | T10-T13 | Telugu/English voice+text assistant completes tasks; scheme Q&A; multi-channel notifications fire.
Sprint 3 | W4 | Module 3 MI + Module 4 Matching | T14-T17 | Demand/price forecasts + hotspots served; buyer recommendations with score & reasons.
Sprint 4 | W5 | Module 5 & 7 Dashboards + Integrations | T18-T21 | Officials monitor via district/ULB/state dashboards + heat maps; MEPMA/ONDC/GeM/Agmarknet wired.
Sprint 5 | W6 | Security/DPDP + Docs + Deploy | T22-T24 | DPDP compliant & hardened; load/E2E passing; documented and deployed to India-region pilot env.

## Tech Stack
Technology Stack
Layer | Technology | Used for
Frontend | React + TypeScript, Vite, Tailwind, PWA | Mobile-first, offline-tolerant SHG UI + all dashboards
Charts / Maps | ECharts/Recharts, Leaflet/Mapbox GL, H3 | Dashboards, heat maps, geo hotspots
Core Backend | Node.js + NestJS | REST APIs, auth, registry, analytics, notifications
AI/ML Services | Python + FastAPI | Serve categorization, NLP, forecasting, recommender
Speech (Telugu/Eng) | Bhashini / AI4Bharat (IndicASR, Indic-TTS) | Voice-to-text and text-to-speech
Telugu NLP | IndicBERT, IndicNLP, spaCy, indic-trans | Intent, entities, transliteration
Forecasting | Prophet / XGBoost / Darts | Demand & price forecasting with seasonality
Recommender | embeddings + FAISS/pgvector, LightFM, LightGBM, SHAP | Buyer matching, ranking, explainability
LLM / RAG | LLM + pgvector RAG | Assistant replies + scheme guidance
Database | PostgreSQL 16 + PostGIS + pgvector | Relational + geo + vector in one engine
Cache / Queue | Redis + BullMQ | Sessions, cache, notification jobs
Messaging | WhatsApp Business API, SMS (MSG91/DLT), IVR (Exotel), Email (SES) | Multi-channel notifications
Integrations | ONDC/Beckn, GeM, Agmarknet (data.gov.in), MEPMA | Catalogue, procurement, prices, SHG master data
Infra / DevOps | Docker, Terraform, GitHub Actions, K8s/Compose | India-region deploy + CI/CD
Observability | Prometheus, Grafana, Loki | Metrics, logs, uptime alerts
Security / DPDP | TLS, KMS, pgcrypto, OWASP ZAP, Snyk | Consent, encryption, audit, hardening

## Legend & Notes
Legend & Notes
Complexity
Low | ~1-2 person-days, well-understood
Medium | ~2-3 person-days, some unknowns
High | ~3-4 person-days, significant build / integration
Very High | 4+ person-days, R&D-heavy or external-protocol risk
Notes
- | Scope is development only: architecture diagrams, technical documents and code. Project-management, procurement, user training, live UAT and demo tasks are intentionally excluded.
- | Tasks are consolidated by module. The 'What To Do' column is the actual implementation checklist for that module component.
- | 6 one-week sprints (Sprint 0-5) run with parallel workstreams. Estimates are effort in person-days, not calendar time.
- | 'Est. (pd)' totals auto-sum on the Sprint Plan tab - edit any estimate and the total recalculates.
- | Dependencies (Depends On) define the build order/critical path across modules.
- | Integrations are live where public APIs exist, otherwise simulated with realistic data.
- | Deployment targets an India-region / MeitY-empanelled host for DPDP Act 2023 data-residency.